## Requirements
requirement_id | category | requirement | priority | sequence_id | dependencies | acceptance_criteria | test_id | status
REQ-CTRL-001 | Controller | Player can move relative to camera using configured directional input | Must | SEQ-001 | Input mapping; character controller | Movement direction matches camera yaw; no movement input causes no horizontal acceleration beyond defined friction | TST-001 | Planned
REQ-CTRL-002 | Controller | Player can sprint while sprint input is held and stamina is available | Must | SEQ-001 | Stamina component | Sprint speed and stamina drain match configured values; sprint stops at zero stamina | TST-002 | Planned
REQ-INT-001 | Interaction | Player can activate the auxiliary power panel within interaction range | Must | SEQ-002 | Interaction detector; panel | Prompt appears in range; one activation changes power state once | TST-003 | Planned
REQ-MSN-001 | Mission | Objective updates when auxiliary power is restored | Must | SEQ-002 | Mission manager; power panel | HUD and mission state update without duplicate completion events | TST-004 | Planned
REQ-AI-001 | AI | Drone transitions through patrol, investigate, pursue, and return/search states | Must | SEQ-003 | Perception; navigation | State transitions match configured conditions and are repeatable | TST-005 | Planned
REQ-LVL-001 | Level | All mandatory objectives are reachable without unintended jumps or collision traps | Must | All | Blockout; collision; navigation | Three complete playthroughs without softlock or unintended out-of-bounds access | TST-006 | Planned
REQ-AUD-001 | Audio | Critical interactions and drone alert have distinct sound feedback | Should | SEQ-002;SEQ-003 | Audio event map | Correct event plays once, at appropriate volume and spatial position | TST-007 | Planned
REQ-UI-001 | UI | Current objective and valid interaction prompt are readable | Must | All | HUD; interaction system | Text is legible at target resolution and does not obscure the center of play | TST-008 | Planned
REQ-NAR-001 | Narrative | Final anomalous reply plays after successful transmission | Must | SEQ-006 | Mission state; dialogue/audio | Final line and subtitle trigger once after transmission completion | TST-009 | Planned
REQ-TECH-001 | Technical | Packaged build launches and can complete the full slice | Must | All | Build settings; assets | Clean launch and full completion on target machine | TST-010 | Planned

## Sequences
sequence_id | title | location | duration_min | purpose | entry_condition | player_objective | key_events | required_assets | exit_condition | failure_retry
SEQ-001 | Arrival & orientation | Docking Airlock | 1 | Establish mood, controls, objective | Mission starts | Reach station interior | EVT_MISSION_START; EVT_AIRLOCK_EXIT | Player, airlock kit, beacon ambience, opening radio | Airlock door opens | Restart at mission start
SEQ-002 | Restore auxiliary power | Service Corridor | 1.5 | Teach interaction and environmental reading | SEQ-001 complete | Activate auxiliary power panel | EVT_PANEL_INSPECTED; EVT_POWER_RESTORED | Power panel, cables, prompt UI, electrical SFX | Power state is ON | Panel remains usable after retry
SEQ-003 | Security drone encounter | Service Corridor | 1.5 | Introduce tension and readable enemy behavior | Power restored | Reach relay chamber; avoid or disable drone | EVT_DRONE_ALERTED; EVT_DRONE_DISABLED or EVT_DRONE_EVADED | Drone model/rig, patrol route, alert SFX, warning lights | Relay door becomes accessible | Checkpoint before encounter
SEQ-004 | Open relay chamber | Relay Chamber Entrance | 0.5 | Connect power puzzle to main objective | Drone encounter resolved | Unlock relay door | EVT_RELAY_DOOR_UNLOCKED | Door, console, light state change | Player enters relay chamber | Door state recalculated on retry
SEQ-005 | Transmit warning | Relay Chamber | 1 | Deliver climax and narrative payoff | Player enters chamber | Activate communications console | EVT_TRANSMISSION_STARTED; EVT_TRANSMISSION_COMPLETE | Console, radio VO, music cue, screen VFX | Transmission completes | Console can be reactivated after retry
SEQ-006 | Anomalous response | Relay Chamber | 0.5 | Create hook for full game | Transmission complete | Listen to response and finish mission | EVT_ANOMALOUS_REPLY; EVT_MISSION_COMPLETE | Final voice line, subtitle, end screen | Mission complete state displayed | Restart or return to menu

## Assets
asset_id | category | name | sequence_or_level | priority | source_format | engine_format | dependencies | owner | status | acceptance_criteria
AST_CHR_001 | Character | Field Operator | All | Must | Blend/FBX | glTF/FBX/native import | Rig; materials; animations | TBD | Planned | Scale, skeleton, materials and required clips validated
AST_ENV_001 | Environment | Docking Airlock Kit | LVL-001 | Must | Blend | glTF/FBX/native import | Materials; collision | TBD | Planned | Modular pieces snap together; collision is clean
AST_ENV_002 | Environment | Service Corridor Kit | LVL-001 | Must | Blend | glTF/FBX/native import | Materials; lights | TBD | Planned | Supports intended path and drone visibility
AST_ENV_003 | Environment | Relay Chamber Kit | LVL-001 | Must | Blend | glTF/FBX/native import | Console; emissive materials | TBD | Planned | Console focal point is readable
AST_PROP_001 | Prop | Auxiliary Power Panel | SEQ-002 | Must | Blend | glTF/FBX/native import | Emissive state materials; interaction | TBD | Planned | ON/OFF states visible and interaction anchor aligned
AST_PROP_002 | Prop | Relay Console | SEQ-005 | Must | Blend | glTF/FBX/native import | Screen material; interaction | TBD | Planned | Activation and transmission states clear
AST_AI_001 | Enemy | Security Drone | SEQ-003 | Must | Blend/FBX | glTF/FBX/native import | Rig; sensor light; AI | TBD | Planned | Silhouette and alert states readable
AST_AUD_001 | SFX | Power panel activation | SEQ-002 | Must | WAV | Engine-supported audio | Audio event map | TBD | Planned | Audible, non-clipping, plays once per activation
AST_AUD_002 | SFX | Drone alert | SEQ-003 | Must | WAV | Engine-supported audio | AI event | TBD | Planned | Clearly distinguishable from ambience
AST_BGM_001 | BGM | Station tension loop | All | Should | WAV | Engine-supported audio | Music bus | TBD | Planned | Loop seamless and does not mask critical cues
AST_VO_001 | Voiceline | Final anomalous reply | SEQ-006 | Must | WAV | Engine-supported audio | Subtitle string | TBD | Planned | Voice and subtitle trigger once and are synchronized
AST_VFX_001 | VFX | Relay transmission effect | SEQ-005 | Should | Engine-native | Engine-native | Console state | TBD | Planned | Readable and within performance budget

## QA Tests
test_id | requirement_id | test_name | preconditions | steps | expected_result | priority | status | notes
TST-001 | REQ-CTRL-001 | Camera-relative movement | Mission loaded; player grounded | Move forward; rotate camera 90 degrees; move forward again | Player moves relative to current camera yaw; diagonal movement is normalized | Must | Not Run
TST-002 | REQ-CTRL-002 | Sprint stamina behavior | Player grounded; stamina full | Hold sprint; continue until stamina is depleted; release and press again | Sprint drains stamina; zero prevents sprint; recovery follows defined rule | Must | Not Run
TST-003 | REQ-INT-001 | Power panel interaction | At service corridor; power OFF | Approach panel; inspect prompt; interact once | Prompt appears in range; panel changes to ON; event fires once | Must | Not Run
TST-004 | REQ-MSN-001 | Objective progression | Power panel available | Activate panel and observe HUD | Objective changes to next task exactly once | Must | Not Run
TST-005 | REQ-AI-001 | Drone state transitions | Drone in patrol state | Enter sight/noise range; break line of sight; wait | Drone investigates/pursues/searches/returns according to rules | Must | Not Run
TST-006 | REQ-LVL-001 | Full level traversal | Clean mission start | Complete all required objectives three times | No softlocks, unintended out-of-bounds access, or unreachable required interactables | Must | Not Run
TST-007 | REQ-AUD-001 | Audio event feedback | Audio enabled; panel and drone available | Activate panel; trigger drone alert | Correct distinct cues play at acceptable level without clipping | Should | Not Run
TST-008 | REQ-UI-001 | Prompt and objective readability | Run at target resolution | Approach panel; view objective during movement | Text is legible and prompt appears only for valid target | Must | Not Run
TST-009 | REQ-NAR-001 | Ending trigger exactly once | Reach relay chamber | Activate console; wait for transmission and reply | Final voice and subtitle play once; mission complete appears | Must | Not Run
TST-010 | REQ-TECH-001 | Packaged build smoke test | Release candidate package available | Launch from clean state; complete slice; restart once | Build launches, completes, and restarts without critical error | Must | Not Run

## Production Gates
gate_id | gate_name | priority | status | exit_criteria | owner | review_date
GATE-01 | Design ready | Must | Planned | Story, scope, sequence list, requirements and risks approved | TBD
GATE-02 | Graybox complete | Must | Planned | Full loop playable with placeholder assets | TBD
GATE-03 | Feature complete | Must | Planned | All Must requirements implemented; no blocker/critical bugs | TBD
GATE-04 | Content and polish | Must | Planned | Assets, audio, lighting, post-processing and performance validated | TBD
GATE-05 | Release candidate | Must | Planned | Must tests pass; packaged build and release notes verified | TBD

## Risk Register
risk_id | risk | likelihood | impact | mitigation | trigger | owner | status
RSK-001 | Scope expands beyond one mission | Medium | High | Keep out-of-scope list visible; defer nonessential features | Feature adds another system/level | TBD | Open
RSK-002 | Drone blocks critical route | Medium | High | Timeout, leash, safe alternate route, checkpoint | Repeated encounter softlock | TBD | Open
RSK-003 | Asset import breaks skeleton/materials | Medium | Medium | Test representative asset early; document export preset | Import warnings or missing tracks | TBD | Open
RSK-004 | Lighting/post-processing hurts readability | Medium | High | Readability review and low-quality preset test | Objective/hazard hard to identify | TBD | Open
RSK-005 | Performance drops in final build | Medium | High | Profile early and after polish | Frame time exceeds target | TBD | Open

## Asset Budget
category | target_count | priority | notes
Player character | 1 | Must | One playable character and minimum locomotion set
Enemy | 1 | Must | One security drone
Playable spaces | 3 | Must | Airlock, corridor, relay chamber
Hero interactables | 2 | Must | Power panel and relay console
Music cues | 2 | Should | Exploration/tension loop and ending cue
Critical SFX | 8 | Must | Door, panel, power, drone alert, steps, transmission, UI, failure
Voicelines | 4 | Should | Opening, power diagnostic, control response, anomalous ending